## Sections
Construction Management - I / Basics of Scheduling | [14 empty] | Time estimates / Bill of quantities
RETAINING WALL - QUANTITIES PER METER
Sect. | Task | Unit | Height of the wall ( H [m] )
|  |  | 1.6 | 1.8 | 2 | 2.2 | 2.4 | 2.6 | 2.8 | 3 | 3.2 | 3.4 | 3.6 | 3.8 | 4
A | Excavating foundation trench | m3 | 0.99 | 1.15 | 1.31 | 1.49 | 1.68 | 1.87 | 2.08 | 2.3 | 2.53 | 2.78 | 3.03 | 3.29 | 3.56
| Refill along the foundation slab | m3 | 0.32 | 0.36 | 0.4 | 0.44 | 0.48 | 0.52 | 0.56 | 0.6 | 0.64 | 0.68 | 0.72 | 0.76 | 0.8
| Embankment building | m3 | 18.1 | 22.83 | 28.23 | 34.19 | 40.73 | 47.84 | 55.52 | 63.77 | 72.59 | 81.99 | 91.95 | 102.49 | 113.6
| Porous backfill behind the wall | m3 | 4.17 | 5.56 | 7.22 | 9.18 | 11.46 | 14.08 | 17.07 | 20.45 | 24.25 | 28.49 | 33.19 | 38.38 | 44.09
B | Sheetwall piling | m2 | 2.67 | 3 | 3.33 | 3.67 | 4 | 4.33 | 4.67 | 5 | 5.33 | 5.67 | 6 | 6.33 | 6.67
| Pulling out sheetwall planks | m2 | 2.67 | 3 | 3.33 | 3.67 | 4 | 4.33 | 4.67 | 5 | 5.33 | 5.67 | 6 | 6.33 | 6.67
| Excavation at the sheetwall | m3 | 5.33 | 6.74 | 8.33 | 10.08 | 11.99 | 14.07 | 16.32 | 18.73 | 21.32 | 24.06 | 26.98 | 30.06 | 33.31
| Excavating foundation trench | m3 | 0.64 | 0.76 | 0.89 | 1.03 | 1.18 | 1.34 | 1.51 | 1.69 | 1.88 | 2.08 | 2.29 | 2.51 | 2.74
| Refill along the foundation slab | m3 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.02 | 0.02 | 0.02 | 0.02 | 0.03 | 0.03 | 0.03
| Porous backfill behind the wall | m3 | 2.13 | 2.65 | 3.22 | 3.85 | 4.54 | 5.29 | 6.09 | 6.95 | 7.86 | 8.83 | 9.86 | 10.95 | 12.09
| Slope ( hollow ) excavation | m3 | 3.84 | 4.86 | 6 | 7.26 | 8.64 | 10.14 | 11.76 | 13.5 | 15.36 | 17.34 | 19.44 | 21.66 | 24
A&B | Grading | m2 | 1.7 | 1.86 | 2.02 | 2.18 | 2.34 | 2.5 | 2.67 | 2.83 | 2.99 | 3.15 | 3.31 | 3.48 | 3.64
| Blinding | m3 | 0.17 | 0.19 | 0.2 | 0.22 | 0.23 | 0.25 | 0.27 | 0.28 | 0.3 | 0.32 | 0.33 | 0.35 | 0.36
| Shuttering foundation slab | m2 | 0.39 | 0.44 | 0.49 | 0.53 | 0.58 | 0.63 | 0.68 | 0.73 | 0.78 | 0.83 | 0.87 | 0.92 | 0.97
| Reinforcing foundation slab | to | 0.02 | 0.03 | 0.03 | 0.04 | 0.05 | 0.05 | 0.06 | 0.07 | 0.08 | 0.09 | 0.1 | 0.11 | 0.13
| Concreting foundation slab | m3 | 0.25 | 0.32 | 0.39 | 0.48 | 0.57 | 0.66 | 0.77 | 0.88 | 1.01 | 1.14 | 1.27 | 1.42 | 1.57
| Shuttering wall, internal | m2 | 1.37 | 1.54 | 1.71 | 1.89 | 2.06 | 2.23 | 2.4 | 2.57 | 2.74 | 2.91 | 3.09 | 3.26 | 3.43
| Reinforcing wall + spout holes | to | 0.02 | 0.03 | 0.03 | 0.04 | 0.05 | 0.06 | 0.07 | 0.07 | 0.09 | 0.1 | 0.11 | 0.12 | 0.13
| Shuttering wall, external + scaffold | m2 | 1.34 | 1.54 | 1.71 | 1.89 | 2.06 | 2.23 | 2.4 | 2.57 | 2.74 | 2.91 | 3.09 | 3.26 | 3.43
| Concreting wall | m3 | 0.27 | 0.34 | 0.42 | 0.5 | 0.6 | 0.7 | 0.82 | 0.94 | 1.07 | 1.2 | 1.35 | 1.5 | 1.67
KERESZTSZELVÉNY
B szakaszon
BUTE DCTM / Engineering Programs in English / 2000- |  | 0.97: Dr. Zoltán András Vattai
10
H/7
20
20
H/7
2/3H
H/10
H/10
20
20
H/7
2/3H
H/10
H/10
10H
10H
3H
10
H/7
H
6/4
5/3H
2H
Section A
Section B
H

## Bill of quantities
Construction Management - I / Basics of Scheduling | [12 empty] | Time estimates / Bill of quantities
Bill of quantities: Retaining wall "…….."; L=…….. m; H=…….. m
Activity |  |  |  | Labour |  |  |  | Equipment* |  |  |  | Duration
ID | Name | Unit | Quantity | Skill | Time Std. | Work | Cap. | Type | Std.Perform. | Work | Cap. | Calc. | Sched.
[5 empty] | [hour/unit] | [hour] |  |  | [unit/hour] | [hour] |  | [hour] | [shift]
1 | Topsoil excavation | m3 | [5 empty] | Dozer
Excavator
2 | Sheetwall piling | m2 |  | Blacksmith | - | - |  | Pile driver
|  |  |  | Labourer | - | - |  | Crawler crane+
3 | Excavation at the sheetwall | m3 | [5 empty] | Excavator
4 | Excavating foundation trench | m3 | [5 empty] | Excavator
5 | Grading | 10m2 |  | Labourer | 3.81
6 | Blinding | m3 |  | Labourer | 4.43 |  |  | Tamper
7 | Reinforcing foundation slab | t |  | Steel fitter | 14.2
|  |  |  | Labourer | 7.6
8 | Shuttering foundation slab | m2 |  | Carpenter | 0.38
|  |  |  | Labourer | 0.09
9 | Concreting foundation slab | m3 |  | Labourer | 1.26 |  |  | Mixer truck+
10 | Dismantle shuttering of foundation slab | m2 |  | Carpenter | 0.1
|  |  |  | Labourer | 0.02
11 | Refill along the foundation slab | m3 |  | Labourer | 0.85 |  |  | Tamper
12 | Shuttering wall, internal | m2 |  | Carpenter | 0.38
|  |  |  | Labourer | 0.09
13 | Reinforcing wall + placing spout holes | t |  | Steel fitter | 14.2
|  |  |  | Labourer | 7.6
14 | Shuttering wall, external + scaffold | m2 |  | Carpenter | 1.43
|  |  |  | Labourer | 0.59
15 | Concreting wall | m3 |  | Labourer | 1.26 |  |  | Mixer truck+
Concrete pump+
16 | Dismantle wall shuttering + scaffold | m2 |  | Carpenter | 0.52
|  |  |  | Labourer | 0.28
17 | Cascading old embankment | m3 |  | Labourer | 1.71 |  |  | Excavator
18 | Embankment building | m3 | [5 empty] | Dozer
Vibro roller+
19 | Porous backfill behind the wall | m3 |  | Labourer | 0.1 |  |  | Excavator
Tamper
20 | Pulling out sheetwall planks | m2 |  | Blacksmith | - | - |  | Pile driver
|  |  |  | Labourer | - | - |  | Crawler crane+
21 | Gutter (drain) construction | m |  | Labourer | 1.41
22 | Slope (hollow) excavation | m3 | [5 empty] | Excavator
23 | Rendering the slope | 10m2 |  | Labourer | 1.02
24 | Levelling the ground | 10m2 |  | Labourer | - | - |  | Grader
25 | Grassing | 10m2 |  | Labourer | 0.4
* Trucks/Lorries and/or power tools (e.g. poker vibrator, saw, bender, etc.) not indicated
+ For further technical parameters and/or estimates see Technical Report
Remarks:
Earth/gravel pit is on …. km distance
Excavated topsoil should be loaded on trucks and sold
Excavated earth can be used for embankment building
For porous backfill, gravel should be added in proportion …....%
Any earth fill should be compacted …. times in not more than …... cm thick layers
Poor viscosity concrete for blinding transported by dumper-truck
Reinforcement bars cut and bended at manufacturing steel-yard …... km away
Concrete mixed at a central batching plant some ……. km away
BUTE DCTM / Engineering Programs in English / 2000- | [12 empty] | Dr. Zoltán András Vattai

## Earth balance
Construction Management - I / Basics of Scheduling | [6 empty] | Time estimates / Bill of quantities
Earth balance calculations: Retaining wall "………..."; L=…... m (…………..); H=……. m
Section "…..."; L=….. m; H=….. m |  |  |  | Section "…..."; L=…… m; H=…... m
ID | Name | Unit | Quantity | ID | Name | Unit | Quantity
1 | Topsoil excavation | m3 |  | 1 | Topsoil excavation | m3
3 | Excavation at the sheetwall | m3 |  | 3 | Excavation at the sheetwall | m3
4 | Excavating foundation trench | m3 |  | 4 | Excavating foundation trench | m3
11 | Refill along the foundation slab | m3 |  | 11 | Refill along the foundation slab | m3
17 | Cascading old embankment | m3 |  | 17 | Cascading old embankment | m3
18 | Embankment building | m3 |  | 18 | Embankment building | m3
19 | Porous backfill behind the wall | m3 |  | 19 | Porous backfill behind the wall | m3
22 | Slope (hollow) excavation | m3 |  | 22 | Slope (hollow) excavation | m3
S |  |  |  | S
Remarks:
Excavated topsoil (of ……..... m3) should be loaded on trucks and sold
Assuming density (compaction) of earth fills should equal to that of original (excavated/natural) earth on site:
- Gravel (of ……...…. m3) to porous backfill is to be brought from the pit …... km away
- For completing porous backfill …………….. m3 is to be brought from the pit ……. km away
For transportation estimated bulking coefficient of earth/gravel is ………..
BUTE DCTM / Engineering Programs in English / 2000- | [6 empty] | Dr. Zoltán András Vattai

## Schedule
Construction Management - I. - REINFORCED CONCRETE RETAINING WALL CONSTRUCTION - Individual Project
SCHEDULE OF WORKS
ID | Task name | [5 empty] | W o r k d a y s
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
1 | Sheetwall piling
2 | Excavation at the sheetwall
3 | Excavating foundation trench, spreading, compacting, grading- and sloping
4 | Shuttering foundation slab
5 | Concreting foundation slab
6 | Dismantle shuttering of foundation lab
7 | Refill along foundation slab in more layers with compaction
8 | Shuttering wall and scaffolding
9 | Concreting wall
10 | Dismantle wall shuttering and scaffolding
11 | Slope (hollow) excavation
12 | Grading before the wall, rendering slope
13 | Embankment building
14 | Grading on the embankment
15 | Porous backfill behind the wall
16 | Pulling out sheetwall planks
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
SCHEDULE OF LABOUR
No | Skill |  |  | Lmax | Lmean |  | 1: W o r k d a y s
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
1. | at site
Labourer at woodyard
Summa
2. | preparatoty works at woodyard
Carpenter shuttering, scaffold, assembly at site
Summa
3. | Blacksmith
4. | Equipment operator
5. | Summa
.
Labour variancy indicatrix :
SCHEDULE OF EQUIPMENT
No | Equipment name | Series | Work |  | Efficience % | pcs | W o r k d a y s 1: W o r k d a y s
|  |  | calculated | applied |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55
1. | Vibratory piledriver (piling)
2. | Mobile crane /….. m beam/
3. | Excavator /…. m3 bucket, front shovel/
4. | Backhoe excavator /…...m3 bucket/
5. | Poker vibrator
6. | Mixer truck
7. | Tamper /………../
8. | Pump truck
9. | Pump truck
10. | Dozer
11. | Vibratory roller compactor
12. | Vibratory piledriver (pull out)
13. | Autocrane