## Blad1
MASTERS IN BUILDING MANAGEMENT
Budapest
TABLE 2: PLANNING DATA
Task | relationship | with | duration per garage unit in workdays
|  |  | A | B | C | D | E | F | G | H | I | J
1 | * |  | 5 | 5 | 5 | 8 | 6 | 7 | 5 | 5 | 5 | 5
2 | finish-finish | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
3 | start-finish | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
4 | start-finish | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
5 | start-finish | 1 and 2 | 2 | 2 | 2 | 5 | 5 | 2 | 2 | 2 | 2 | 2
6 | start-finish | 4 | 5 | 4 | 7 | 6 | 6 | 5 | 6 | 4 | 7 | 6
7 | finish-finish | 1 | bar: duration per garage unit in workdays A to duration per garage unit in workdays J
8 | start-finish | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
* task 1 commences for the first unit to be built on the date of commencement of the work: 21/03/2005
for the 2nd and following units, task 1 starts as soon as possible after the completion of task 1 of the last unit and depending
on the most beneficial planning, ensuring each unit, as soon as started, has a minimum of downtime
the contractors can never work at two places at the same time
there is no continuity provided for the work of each contractor
task 4: always takes place for 2 customers on the same day
start: commencement of the following task
finish: end of the last task
when drawing up the planning one best uses different shading per task