## Blad1
example 2: concrete river tube
Descriptif measurement
Number of Item | Description | sort | unit | Quantity
1 | Dig of of vegetable mould and take in stock for re-use | P.Q. | m³ | 80
2 | Fill-up of vegetable mould | P.Q. | m³ | 80
3 | Dig out of sandy ground, partial in stock for re-use, partial to move away of the site | P.Q. | m³ | 520
4 | Fill-up of sandy ground from the stock | P.Q. | m³ | 80
5 | Evacuation of rest of ground | P.Q. | m³ | 450
6 | Furnishing and work-up of concrete C10/16, included form-work | P.Q. | m³ | 25
7 | Furnishing and work-up of concrete C25/30, included formwork | P.Q. | m³ | 150
8 | furnishing and placing of the joint between the sections | P.Q. | CM | 50
9 | Draining of the excavation | LS
10 | Furnishing und placing of the reinforcement steel | P.Q. | kg | 22500
codes of measurement:
- earthwork: vertical projection of the work + 50 cm around - vertically slope
- concrete: volume in the formwork
- joints: real lenght joining
- reinforcement steel: net quantity for stability