## Blad1
example 1: direct cost of a concrete slab for a bridge
Project: xxxxx |  | Number: xxxxxx |  |  |  | Direct cost/item
Client:xxxxx
Date: xxxxx
Nr | Description | U | Quant | Hours labour |  | Direct cost
Item/ |  |  |  | norm | quantity | by unit (task) |  |  |  |  | total
task | [5 empty] | 17796.5 | Wages | Engins | Subc. | Tot. | Mat. | Wages | Engins | Subc. | Tot.
item 7 | Concrete for bridge slab | m³ | 210
7.a | Profile foundation ground | m² | 210 | 10m²/h | 21 |  | 2 |  |  | 2 |  | 420 |  |  | 420
7.b | Scaffolding towers
| assemblage + 1 month | p | 16 | [5 empty] | 80 |  |  |  |  | 1280
| hire | pxm | 16x2 | [5 empty] | 70 |  |  |  |  | 2240
| take away | p | 16 | [5 empty] | 40 |  |  |  |  | 640
[9 empty] | 190 | 260 |  |  |  | 4160 | 4160
7.c | foundation slabs | p | 64 | 0.2 |  | 5 |  |  |  |  | 320
| work | p | 64 | 5p/h | 12.8 |  | 4 |  |  |  |  | 256
| crane | d | 1 |  |  |  |  | 520 |  |  |  |  | 520
[10 empty] | 17.125 | 320 | 256 | 520 |  | 1096
7.c | Formwork
| beams 8/23 | m | 288 | 0.5 |  | 3.25 |  |  |  |  | 936
| beams 7.18 | m | 972 | 0.5 |  | 2.75 |  |  |  |  | 2673
| plates | m² | 350 | 0.25 |  | 3.75 |  |  |  |  | 1312.5
| work: place | m² | 350 | 1h/m² | 350 |  | 20 |  |  |  |  | 7000
| work: take away | m² | 350 | 0.5h/m² | 175 |  | 10 |  |  |  |  | 3500
| ends | m | 30 | [5 empty] | 8 |  |  |  |  | 240
| left and rigjt | m | 40 | [5 empty] | 11 |  |  |  |  | 440
| crane | day | 2 |  |  |  |  | 520 |  |  |  |  | 1040
[6 empty] | 9.75 | 30 | 520 | 19 | 48.976 | 4921.5 | 10500 | 1040 | 680 | 17141.5
7.d | concrete
| furnishing | m³ | 192 |  |  | 65 |  |  |  |  | 12480
|  | m³ | 1 |  |  | 75 |  |  |  |  | 75
| pumping | LS | [6 empty] | 250 |  |  |  |  | 250
|  | m³ | 193 | [5 empty] | 6.3 |  |  |  |  | 1215.9
| work | m³ | 193 | 0.5h/m³ | 96.5 |  | 10 |  |  |  |  | 1930
[6 empty] | 140 | 10 |  | 256.3 | 82.647 | 12555 | 1930 |  | 1465.9 | 15950.9
7.e | finishing | m² | 300 | 0.5h/m³ | 150 |  | 10 |  |  |  |  | 3000 |  |  | 3000
| Total item |  |  |  | 805.3 |  |  |  |  | 216.42 | 17796.5 | 16106 | 1560 | 6305.9 | 41768.4
Transfer
New Total
| 41768.40 : 193 = 216.42 |  |  | 1.088
41768.40 : 210 = 198.90